## Tasks
Task ID | Category | Title | Description (if more detail than title) | Source
EHRs
1-01 |  | Explore Statewide Electronic Health Record (EHR)/Rural EHR | HCA will take initial steps to explore: (i) how best to promote the adoption of certified electronic health record (EHR) technology for providers that do not use certified EHR solutions or do not have needed functionality to support caregiving. Particular focus includes rural, behavioral health, Department of Corrections/jails providers, and/or tribal providers; and (ii) identify potential funding sources and pursue viable option(s). This effort may lead to the development of request for information or potentially an request for proposals to connect these technology solutions with providers needing them.
1-02 |  | Administer EHR Incentive Project | Continue to support HITECH EHR incentive payments to eligible hospitals and professionals. Support is expected to continue through the end of the designated audit funding period for HITECH. | 2019 project continuing
1-03 |  | Webinar on CEHRs and HITECH EHR Incentive Program. | Q1: HCA HIT Section will provide a recorded webinar providing training on a primer of what is a certified EHRs and provide basics of HITECH EHR Incentive Program. The Webinar will also address Public Health Registry Onboarding under the Promoting Interoperability Program.
Mental Health IMD Waiver
2-01 |  | Required MH IMD Waiver Attestation | As part of the MH IMD Waiver application, HCA will attest that the state has a sufficient health IT infrastructure/ecosystem at every appropriate level (i.e. state, delivery system, health plan/MCO and individual provider) to achieve the goals of the demonstration. If this is not yet the case, please describe how this will be achieved and over what time period | MH IMD Waiver Statement 1: Please provide an assurance that the state has a sufficient health IT infrastructure/ecosystem at every appropriate level (i.e. state, delivery system, health plan/MCO and individual provider) to achieve the goals of the demonstration. If this is not yet the case, please describe how this will be achieved and over what time period
2-02 |  | Required MH IMD Waiver Attestation | As part of the MH IMD Waiver application, HCA will attest that the state's SUD Health IT Plan is aligned with the state’s broader State Medicaid Health IT Plan and, if applicable, the state’s Behavioral Health IT Plan. If this is not yet the case, please describe how this will be achieved and over what time period. | MH IMD Waiver Statement 2: Please confirm that your state’s SUD Health IT Plan is aligned with the state’s broader State Medicaid Health IT Plan and, if applicable, the state’s Behavioral Health IT Plan. If this is not yet the case, please describe how this will be achieved and over what time period.
2-03 |  | Required MH IMD Waiver Attestation | As part of the MH IMD Waiver application, HCA will attest that the state intends to assess the applicability of standards referenced in the Interoperability Standards Advisory (ISA) and 45 CFR 170 Subpart B and, based on that assessment, intends to include them as appropriate in subsequent iterations of the state’s Medicaid Managed Care contracts. The ISA outlines relevant standards including but not limited to the following areas: referrals, care plans, consent, privacy and security, data transport and encryption, notification, analytics and identity management. | MH IMD Waiver Statement 3: Please confirm that the state intends to assess the applicability of standards referenced in the Interoperability Standards Advisory (ISA) and 45 CFR 170 Subpart B and, based on that assessment, intends to include them as appropriate in subsequent iterations of the state’s Medicaid Managed Care contracts. The ISA outlines relevant standards including but not limited to the following areas: referrals, care plans, consent, privacy and security, data transport and encryption, notification, analytics and identity management.
2-04 |  | Financial map for BH HIT Plan | HCA (DBHR and HIT) will develop a financial map that identifies sources of funds (e.g., Decision package (DP), MMIS, CMS grants, SAMHSA Grants) to execute the HIT/HIE activities required in the MH HIT Plan in the MH IMD Waiver. Note: Timeline reflects when deliverable is due to CMS. HCA anticipates financial mapping will be an ongoing activity. | MH IMD Waiver State Medicaid programs should detail plans to support improved availability of non-hospital, non-residential mental health services including crisis stabilization and on-going community-based care. The financing plan should describe state efforts to increase access to community-based mental health providers for Medicaid beneficiaries throughout the state, including through changes to reimbursement and financing policies that address gaps in access to community-based providers identified in the state’s assessment of current availability of mental health services included in the state’s application. F.a Increase availability of non-hospital, non-residential crisis stabilization services, including services made available through crisis call centers, mobile crisis units, observation/assessment centers, with a coordinated community crisis response that involves collaboration with trained law enforcement and other first responders. F.b Increase availability of on-going community-based services, e.g., outpatient, community mental health centers, partial hospitalization/day treatment, assertive community treatment, and services in integrated care settings such as the Certified Community Behavioral Health Clinic model.
2-05 |  | Closed Loop Referrals and e-Referrals: | Contingent on funding, the State will complete the following: 1. As required in MH IMD Waiver, identify opportunities to support /advance interoperable close-loop referral between: (a) hospital and physician (b) physician to MH (c) by physician/mental health provider to community-based organizations (CBOs) 2. HCA staff (e.g., CQCT/HIT Section and Clinical; and Policy) will participate in ACH/CM Workgroup to support/advance the use of CM ADTs from hospital to community-based providers (assumes inclusion as part of ACH/CM Workgroup activities. HCA funds are not available to support community-based mental health providers' use of these tools). 3. HCA/HIT Section staff in collaboration with ACH staff will support close loop referral (e.g., Digital Health Commons). For example: support activities could include: (i) potentially disseminating information by leveraging HIT Operational Planning meeting time; (ii) HCA Policy and HIT Section staff providing Data Exchange guidance / direction regarding: closed loop referral, statewide direction (e.g., single platform vs. community-based approach), information regarding key HIT standards/policies/tools that support exchange between providers/networks) 4. HIT Section staff collaborate with ONC and ACHs to identify opportunities for ACHs and provider partners to pilot (potentially funding sources may need to be identified). Pilot opportunities include: 360X and potential Gravity Project pilot). | MH IMD Waiver 1.1 Closed loop referrals and e-referrals from physician/mental health provider to physician/mental health provider 1.2 Closed loop referrals and e-referrals from institution/hospital/clinic to physician/mental health provider 1.3 Closed loop referrals and e-referrals from physician/mental health provider to community based supports
2-06 |  | Create and use Electronic Care Plans that are interoperable | Contingent on funding, the State will complete the following: 1. HIT Section will contract to gather information on use of electronic/interoperable care plans by BH, including MH providers 2.HIT Section and Policy staff will coordinate with Medicaid Managed Care Organizations (MMCOs) via a workgroup to develop a shared care plan template. This may include a shared care plan for clinical services and a separate shared care plan for social service. 3. HIT Section, Policy, CQCT, and DBHR staff will coordinate with Department of Corrections and jails to consider the need for and if needed, the use of care plans between health care providers in jails/prisons and community-based health providers. | MH IMD Waiver 2.1 The state and its providers can create and use an electronic care plan 2.2 E-plans of care are interoperable and accessible by all relevant members of the care team, including mental health providers
2-07 |  | Medical Records Transition. | Contingent on funding, the State will complete the following: 1. Identify best practice standards for transition planning from inpatient and residential care prior to discharge 2. Consider strategies to incentivize discharge outcomes that ensure housing stability 3. Advance recommendations to implement best practices for successful discharge planning 4. HCA Policy staff explore opportunities to support information exchange on behalf of incarcerated persons 30 days prior to release. 5. HIT Section, in coordination with HCA/Policy, DBHR, and Data Governance staff, will explore opportunities and approaches to support creation, exchange, and access of CCDs/other health records including (i) from youth oriented systems of care to and from adult systems of care and (ii) on behalf of incarcerated persons, including: - TA to providers re: creation, exchange and access to CCDs via CDR - TA to providers re: view/download PAMI from CDR - Access to CCDs/Problems/Allergies/Medications/Interventions by health providers upon incarceration 6. HCA DBHR staff, in coordination with MPOI and HIT Section staff, will work to align these MH IMD Waiver requirements with MMC requirements. | MH IMD Waiver 2.3 Medical records transition from youth-oriented systems of care to the adult behavioral health system through electronic communications 2.4 Electronic care plans transition from youth-oriented systems of care to the adult behavioral health system through electronic communications 2.5 Transitions of care and other community supports are accessed and supported through electronic communications MMC IMC contract language: 14.1.9 Continuity and Care Coordination for Transition Age Youth (TAY): 14.1.9.1 The Contractor shall develop a comprehensive transition plan in collaboration with other systems and providers, including agencies contracted to provide services to Youth, that identifies the Enrollee’s goals, objectives, and strategies to achieve goals. The transition plan shall take into account the following: 14.1.9.1.1 Individual behavioral and physical health needs, which may include continued services in the adult behavioral or physical health systems. The transition plan shall address the need for continuity and coordination of services and supports for the Enrollee and the Enrollee’s family and identify developmentally and culturally appropriate adult services; 14.1.9.1.2 Connections with supportive housing and supported employment services through the Foundational Community Supports program, post-secondary education, technical training, housing community support, natural supports, and cross-system coordination as needed to attain the Enrollee’s goals. 14.13.14 Prioritizing WISe For Youth Discharging From CLIP: The Contractor must prioritize access to WISe services for all youth qualified to receive WISe services that are discharging from CLIP. 14.13.15 Rehabilitation Case Management (RCM): The Contractor must provide Rehabilitation Case Management (RCM) throughout the entirety of the CLIP treatment from preadmission through discharge. RCM includes a range of activities conducted in or with a facility for the direct benefit of the admitted youth to improve treatment gains and plan for successful discharges from CLIP. Activities include: 14.17.3.1 The Contractor must complete the Uniform Discharge Tool reporting template for every individual discharging from a mental health inpatient setting hospital stay. The template, developed collaboratively with contracted MCOs and HCA, will be finalized by the end of the first quarter of 2019 and submitted afterward as described below: ... 14.17.3.5 The Contractor, in collaboration with all hospitals including state hospitals; and other facilities that provide care for individuals with 90 and 180-day civil commitments, shall develop discharge planning policies and procedures. 14.17.3.5.4 The Contractor must accept the ’honor authorization’ for SUD residential admission when services are authorized by the Enrollee’s previous MCO, in cases where an incarcerated Enrollee is authorized by one MCO but changes to another MCO upon release. 14.17.4 Care coordination and transitions between levels of care – Inpatient Treatment Agencies. 14.17.4.1 The Contractor must require that behavioral health treatment agencies develop policies and procedures that enhance care coordination, including transitions between all levels of care, by July 1, 2019. Any new policies or procedures must take effect on or before October 1, 2019. 14.17.4.2 The Contractor must work with behavioral health treatment agencies to ensure there is adequate coordination for Enrollees transitioning between various levels of treatment services to ensure continuity of care. As used in this section, “continuity of care” means the situation under which an Enrollee who is receiving services from an individual provider is entitled to receive timely and applicable follow-up services from ancillary referral agencies with the goal of providing immediate follow-up to address the holistic needs of the Enrollee. This will include, at a minimum, the following: 14.17.4.3 The Contractor must work with the Subcontractor to ensure that discharge plans and facilitation to post-discharge services are documented in the Enrollee’s electronic health record. The following must occur when the Enrollee is discharged or transitioned to a lower or higher level of care: 14.17.4.3.1 Appropriate referrals are made to a behavioral health provider and coordination with the Enrollee’s MCO. 14.17.4.3.2 Follow up appointments must be scheduled to occur within seven calendar days of Enrollee discharge and documented as such in the Enrollee’s electronic health record. Documentation must include: 14.17.4.3.2.1 Release of Information between behavioral health treatment agencies for the Enrollee; date and time of appointment; any current medications; and 14.17.4.3.2.2 If applicable, sufficient supply and compliance plan for prescribed medications is documented as part of the discharge process. 14.17.4.3.3 Enrollee’s counselor or a designated outreach coordinator at the facility, will follow up via telephone, text message, or email with the Enrollee within one week post-discharge. 14.17.5 Transition from Inpatient SUD Behavioral Health Agency. The Contractor must coordinate with Subcontractors who provide inpatient treatment to ensure referrals of Enrollees to outpatient services post-discharge from their facility. This includes the following:... 14.17.5.2.1.4 Housing. Enrollee’s housing status must be verified through the Enrollee or authorized representative and documented within the electronic health record system. When necessary, the Behavioral Health facility will refer Enrollee to housing and community support services; documentation of any referrals must be placed in the electronic health record. When the Enrollee is prescribed FDA approved medications for SUD, the provider must document efforts to obtain housing to fit the individual’s needs. 14.17.5.2.1.5 Transportation- Arrange for transportation for the individual, as needed, to scheduled appointments and recovery-based housing.
2-08 |  | Consent - E-Consent (sharing of sensitive health care information to all relevant parties consistent with applicable law and regulations (e.g., HIPAA, 42 CFR part 2 and state laws)) | Contingent on funding, the State will complete the following: 1. HCA HIT Section will enter into contracts to support: - Development of TA materials for SUD/MH providers re: privacy requirements (related to 42 CFR Part 2) - SUD provider workflow related to consent - vendor procurement and system development for consent management solution - pilot of a consent management solution 2.HCA HIT Section seek continued funding to expand consent management past pilot | MH IMD Waiver 3.1 Individual consent is electronically captured and accessible to patients and all members of the care team, as applicable, to ensure seamless sharing of sensitive health care information to all relevant parties consistent with applicable law and regulations (e.g., HIPAA, 42 CFR part 2 and state laws) Funding Source: Support Act APD/ Sec. 5042
2-09 |  | Interoperable Intake, Assessment, and Screening tools: data is interoperable with the rest of the HIT ecosystem | Contingent on funding, the State will complete the following: 1. HIT Section will contract to gather information on additional data sources including use/barriers/ options to encourage use of: PMP, Methadone Registries, and use of electronic/interoperable care plans, electronic assessment/screening/ intake tools 2. Coordinate w/ ONC and CMS and other states to standardize selected intake assessment and screening tools. 3. Link standardized care plans, electronic assessment/screening/ intake tools with HIT standards. 4. Create FHIR enabled interoperable tools that would support the exchange of care plans, electronic assessment/screening/ intake tools. 5. Pilot use of the FHIR-enabled interoperable care plans, electronic assessment/screening/ intake tools. | MH IMD Waiver 4.1 Intake, assessment and screening tools are part of a structured data capture process so that this information is interoperable with the rest of the HIT ecosystem the rest of the HIT ecosystem Funding Source: Support Act APD/ Sec. 5042
2-10 |  | Telehealth | Contingent on funding, the State will complete the following: 1. HCA/Policy and HIT Section will explore (i) Medicaid Managed Care (MMC) coverage and payment policies regarding telehealth and (ii) activities being undertaken by the UW related to telehealth to identify whether there are gaps that need to be filled and options for addressing these gaps 2. Q1 - Q4: HCA/CQCT/Clinical Policy staff will leverage and analyze information emerging via the following workgroups to help inform telehealth coverage policies to support access to high quality services: - NASHP convened Telehealth Affinity Group of policymakers and stakeholders to learn about the Patient Centered Outcomes Research Institute (PCORI)'s emerging telehealth research and explore associated policy challenges and solutions - MED Telehealth workgroup (a forum for state agencies) to discuss telehealth issues facing Medicaid programs including coverage policies, utilization, expenditures, patient privacy and security, and patient outcomes. The workgroup also explores best practices and evidence related to telehealth and monitors emerging telehealth advancements that may be relevant to Medicaid agencies. 3. Identify, disseminate, and promote information on telehealth, including grant opportunities | MH IMD Waiver 5.1 Telehealth technologies support collaborative care by facilitating broader availability of integrated mental health care and primary care Rural Health EHR
2-11 |  | Analytics: the state can identify patients at risk for discontinuing/stopping treatment and alerting care teams | DBHR staff in collaboration with HIT Section will explore options for identifying patients at risk discontinuing/stopping treatment and methods for alerting care team members. | MH IMD Waiver 6.1 The state can identify patients that are at risk for discontinuing engagement in their treatment, or have stopped engagement in their treatment, and can notify their care teams in order to ensure treatment continues or resumes (Note: research shows that 50% of patients stop engaging after 6 months of treatment ) MMCO IMC Contract language: 14.17.5.3 If the Enrollee discontinues services, the Subcontractor will document as such and attempt to facilitate transition back into the community.
2-12 |  | Health IT is being used to advance the care coordination workflow | Contingent on funding, the State will complete the following: - HIT Section, Policy, and MPOI will collaborate to identify health IT/health information exchange tools that could support care coordination workflow of HCA, payers, and providers and options for developing needed tools; and - HIT Section and DBHR will identify the providers involved in caring for persons experiencing their first episode of psychosis, the workflow involved, and the technical tools needed to support care coordination on behalf of these individuals. | MH IMD Waiver 6.2 Health IT is being used to advance the care coordination workflow for patients experiencing their first episode of psychosis
2-13 |  | Electronic medical records capture all episodes of care, and are linked to the correct patient | Contingent on funding, the State will complete the following: HIT Section will coordinate with the Office of the National Health Coordinate for HIT (ONC) to identify technical solutions for linking, when appropriate, EMRs of children and parents. HIT Section will begin collaboration with HCA Chief Data Officer and Data Governance to identify policies that will need to be addressed to enable linkage between parent and child EMRs | MH IMD Waiver 7.1 As appropriate and needed, the care team has the ability to tag or link a child’s electronic medical records with their respective parent/caretaker medical records
2-14 |  | Identity Management | Contingent on funding, the State will complete the following: the care team links a child’s electronic medical records with their respective parent/caretaker medical records Develop strategic plan to identify tasks that will move towards enable linking child's and parent's EMRs - Gathering information re: the instances of linking child's identity w/ parent's - link to ongoing MPI work | MH IMD Waiver 7.2 Electronic medical records capture all episodes of care, and are linked to the correct patient
SUD HIT Plan and PDMP Enhancements
3-01 |  | B. Enhanced interstate data sharing in order to better track patient specific prescription data | Ongoing in each Quarter: - DOH will assess and potentially add additional states through the Rxcheck/or PMPi Hubs. As more states join Rxcheck/or PMPi, DOH will work to include data from these states by WA providers. - DOH will assess and evaluate feasibility of adding interstate data sharing queries through the HIE or EHR integration. | SUD IMD Waiver Enhanced interstate data sharing in order to better track patient specific prescription data Funding Source: Section 5042 Support Act APD
3-02 |  | C. Enhanced “ease of use” for prescribers and other state and federal stakeholders | Q1: DOH will outline for the system users (e.g., licensing officials, prescribers, law enforcement officials) some of the improvements that offered by the Aware Platform. Q2: The new platform is scheduled to go live in April 2020. Q1: DOH anticipates completing a security review. (In 2019, DOH has begun a security review of the OHP SSO to see if it can be approved for potential use by the PDMP and other programs. This also could potentially allow HCA to provide access to PDMP data via the CDR). Q1: OHP and Appriss (the PDMP vendor) have the new version of NCPDP (2017071) available production in Q1 2020. | SUD IMD Waiver Enhanced “ease of use” for prescribers and other state and federal stakeholders
3-03 |  | D. Enhanced connectivity between the state’s PDMP and any statewide, regional or local health information exchange (Timeline 24+ months). DOH will solicit proposals and secure a vendor to develop an API (that meets required HIT standards (NCPDP SCRIPT V. 2017-071)) for PDMP / HIE connections, including interstate data sharing of PDMP data; | The Department of Health will complete the following activities: Q1: Leveraging the results of the assessments undertaken in 2019, DOH leadership will consider feasibility of the use of the HIE-only vs. HIE plus other 3rd party integrators to support PMP/EHR integration. Q2: DOH will begin work in the to develop an RFP for the PDMP system. The RFP will integrate with the state HIE using updated standards and interstate data sharing will be included. Q3-Q4 DOH anticipates releasing an RFP for the PDMP system. | SUD IMD Waiver Enhanced connectivity between the state’s PDMP and any statewide, regional or local health information exchange
3-04 |  | E. Enhance identification of long-term opioid use correlated to clinician prescribing patterns | Through a collaboration via Better Prescribing and Better Treatment (BPBT) (WSMA, WSHA, HCA, DOH) the group will: • Refine metrics for prescriber feedback reports (CY 2019) • Q1 Disseminate quarterly provider feedback reports in • Q1 reconvene discussion to update status metrics for CMO reports | SUD IMD Waiver Enhanced identification of long-term opioid use directly correlated to clinician prescribing patterns48 (see also “Use of PDMP” #2 below)
3-05 |  | G. Develop enhanced provider workflow / business processes to better support clinicians' access to the PDMP prior to prescribing an opioid or other controlled substance (Timeline: 12 months) | Leveraging a Department of Health Comagine contract. Q1 - Q3: The Comagine team will complete the following activities: Gather information to help inform DOH and HCA of the enablers and barriers to integration of PMP information into EHRs and help inform work on the FHIR application, as well as the requirements for a PMP to support this functionality. | SUD IMD Waiver Develop enhanced provider workflow / business processes to better support clinicians in accessing the PDMP prior to prescribing an opioid or other controlled substance to address the issues which follow
3-06 |  | H: Develop enhanced supports for clinician review of the patients’ history of controlled substance prescriptions through the PMP— prior to the issuance of an opioid prescription (Timeline: 24+ months) | see row 26 above. | SUD IMD Waiver Develop enhanced supports for clinician review of the patients’ history of controlled substance prescriptions provided through the PDMP—prior to the issuance of an opioid prescription
3-07 |  | F. Facilitate the state’s ability to properly match patients receiving opioid prescriptions with patients in the PDMP (i.e. the state’s master patient index (MPI) strategy with regard to PDMP query) | Contingent on the availability of funds, work with Health and Human Services multi-agency Enterprise Governance (EG) process (e.g., HCA, DOH, DSHS, DCYF, HBE) to: • Q2: Include the PDMP use case on the MPI implementation roadmap • Q4: draft a project scope that facilitates patient/provider matching. • Q4: Present draft scope to EG Exec. Sponsors • 2021: Upon project completion (and contingent on funding) proceed w/ implementation | SUD IMD Waiver Facilitate the state’s ability to properly match patients receiving opioid prescriptions with patients in the PDMP (i.e. the state’s master patient index (MPI) strategy with regard to PDMP query)
3-08 |  | Task I: Enhance MPI (or master data management service, etc.) in support of SUD care delivery | Contingent on the availability of funds, work with Health and Human Services multi-agency Enterprise Governance (EG) process (involving HCA, DOH, DSHS, DCYF, HBE) to: • Q2: include SUD use cases in the MPI implementation roadmap • Q4: draft a project scope that facilitates patient/provider matching. • Q4: Present draft scope to EG Exec. Sponsors • 2021: Upon project completion (and contingent on funding) proceed w/ implementation | SUD IMD Waiver Enhance the master patient index (or master data management service, etc.) in support of SUD care delivery.
3-09 |  | eConsent Management Tool | Q3 - Q4: HCA will develop and pilot an electronic consent management solution that can be used to support the exchange of information subject to 42 CFR Part 2 and allow for the appropriate redisclosure of this information. (see row 13) | 2019 project continuing
Master Person Index
4-01 |  | Begin Proof of concept for MPI | Contingent on the availability of funds, the HHS Coalition will conduct the following activities: •Develop MPI implementation roadmap with options for Limited MPI implementation through full development of MPI as a system of record for participating systems •Develop RFP for MPI/tool with capability to support increasing levels of MPI functionality over a multi-stage phased implementation •Implement a proof of concept of foundational technologies and limited MPI (the scope of which will be determined during the initial planning process) •Develop the framework for data and system governance for the MPI. This frame will need to be scalable as additional systems and agencies connect to the MPI. | 2019 project continuing
Provider Directory
5-01 |  | Draft Provider Directory white paper and implementation plan for Enterprise Governance decision making | Q2: The HIT Section will draft a Provider Directory White Paper in pursuit of HCA's VBP goals/achieving the quadruple aim and for project prioritization decision making for the Health and Human Services multi-agency Enterprise Governance (EG) process (involving HCA, DOH, DSHS, DCYF, HBE). The draft Provider Directory White Paper will take into account need for such directory (e.g., use of a Provider Directory in the PDMP) and will take into account input from non-state entities selected by HCA for an advisory role given their work on similar provide directory efforts. | 2019 project continuing
5-02 |  | Time and distance standards for provider networks | Q1 - Q2: HCA HIT section staff, in collaboration with other HCA staff (e.g., DBHR, ARM, MPOI staff), will send an email to MCOs in January requesting workgroup participants in monthly, 1 hour meetings from February - July. The purpose of the workgroup is to focus on MMC contracting requirements for Geo-Coding (Section 6.22) that requires the Contractor, in collaboration with the HCA, to consider the availability and adequacy of needed tools (e.g., SAMHSA service locator, other tools) for and feasibility and value of implementing geo-coding to enhance clinical and administrative decision making. During the monthly meetings, MMCO participants will bring information and recommendations from their organization about how to advance the use of a shared, statewide geo-coding platform. | MMCO Contract language (effective 1/2020) MMC 6.22.1 The Contractor, in collaboration with the HCA, shall consider the availability of needed tools for, and feasibility and value of implementing geo-coding to enhance clinical and administrative decision making for and service delivery to targeted populations (e.g., persons SUD/OUD). The Contractor shall take into account the location of: (i) physical and behavioral health providers; (ii) ancillary providers (e.g., pharmacy); (iii) social services; and (iv) other services needed to address the needs of the targeted population. MMC 6.22.2 The Contractor shall submit a report to participate in a workgroup with HCA no later than July 1 that identifies and prioritizes opportunities to implement geo-coding for use by Medicaid beneficiaries, network providers, and the Contractor. The report workgroup shall consider how to address regional provider and service needs and the benefits of a statewide geo-coding infrastructure.
Payment Models and Sources
6-01 |  | Provider Assignment/Provider Attribution | Q1 - Q4: HCA Policy and HIT Section staff will (i) identify patient /provider attribution methodologies used by MCOs to assign patients to providers, (ii) gather information from MCOs and ACHs as to why patient/ provider attribution is a barrier for VBP, (iii) identify options that could be pursued to address barriers and reduce inconsistencies between MCOs, (iv) develop an HCA standard for deployment of consistent and aligned attribution methodologies for the purposes of VBP arrangements among payers, providers, and ACHs, and (v) review MCO client assignment files for completeness and accuracy and (vi) identify options to leverage MCO client assignment files to support providers understand their patient populations and advance VBP. | Managed Care Contract language: Requirement in Section 6.22 of the MCO contracts "Enrollee PCP Assignment Files"
6-02 |  | VBP Models and HIT/HIE | HCA/Policy staff will: • Analyze for either global VBP system and/or project specific VBP models whether base year payment calculations take into account HIT/HIE costs for providers participating in VBP models; and • Identify VBP payment methods that create incentives for providers to use HIE technology to send/receive data (including to the CDR) for identified use cases (e.g., transitions in care). Policy staff will submit to HCA policy leadership findings of analysis and take action as appropriate. | 2019 project continuing
6-03 |  | Implement Payment Model 2-Rural Multipayer Payment Model | Contingent on availability of funding and HCA leadership approval, HCA Policy and HIT Section staff will develop an RFI/RFP for EHR requirements needed for rural providers, the RFI/RFP could support implementation of VBP incentives in Rural Multi-payer Payment Model that includes incentives to use HIE technology to send/receive data to the CDR and other functionality. | 2019 project continuing
6-04 |  | APM for SUD | Q3 - Q4 (and into CY 2021): As required in Section 1003 CMS funding opportunity (aka Roadmap for Recovery), HCA staff, in collaboration w/ selected Contractor, will design and develop an SUD APM that incorporates social determinants of health (SDoH) factors and HIT incentives | Section 1003 Funding: CMS Cooperative Agreement
Data and Governance
7-01 |  | Develop process for incorporating successes from evaluation work (SIM, MTP, etc.) | Question: Should this be rescoped to focus on MTP evaluation work? | 2019 project continuing
7-02 |  | Data Strategy | The HIT Section will support and leverage the HCA Data Strategy to inform the HIT activities.
7-03 |  | Advancing/supporting care coordination | Q1 - Q4: Leveraging the priorities approved by the Medicaid Transformation Priorities Steering Committee, staff in HCA Policy in collaboration with other HCA staff (e.g., staff in HIT Section, CQCT) will seek to advance needed care coordination activities in the following three workstreams: Optimize Health Homes Engagement, Community Information Exchange, and Centralized Care Coordination Facilitation. Staff in each workstream will identify: key decision points, action items, dependencies, and timelines for consideration and approval by the Steering Committee. | 2019 project continuing
7-04 |  | ACH Sustainability | HCA Policy to articulated what ACH models/activities could be sustainable post-MTP, including use of HIT tools.
Health Information Exchange functionality, including enhancing the CDR
8-01 |  | Supporting shared HIT/HIE needs across ACHs. | HCA HIT Section and Policy staff will: - based on a review of ACH submitted documents, consult with ACHs to better understand some of the shared needs identified across several ACHs (e.g., shared Care Plans, Population Health Management, Closed Loop Referral); - work with ACH and providers to identify a few highly desirable modes of HIT/HIE technical support by provider type ( i.e., PCPs vs BH); and - identify activities and funding sources that could be leveraged to support sustainable shared HIT/HIE needs and technical support for providers across ACHs. | 2019 project continuing
8-02 |  | Closed loop referral, e-Consults, and Population Health Management | Q1 - Q4: HCA HIT Section and Policy staff, in consultation with ACHs and their partnering providers (e.g., acute care, primary care, BH, FQHC, jails), and other stakeholders will produce written descriptions of: (i) emerging / best practices across communities to provide HIT-enabled integrated person-level care, and (ii) opportunities for shared /sustaining investments. White papers will be developed describing practices and opportunities to provide HIT-enabled integrated person-level care for: e-consults, close-loop referral processes, identify and stratify high risk patients, and support health information sharing. | See MH IMD Waiver task (row 11)
8-03 |  | MMC Population Health Management: Plan | Q2 -Q3 HCA Policy staff in collaboration with staff in the HIT Section, ARM and DBHR, shall review MMCO Population Health Management plans to gather information about how plans coordinate care and manage care on behalf of Medicaid beneficiaries with emerging risks, multiple chronic conditions, and received care and services from providers across the care continuum. HCA staff will summarize information from the MMCO Population Health Management plans regarding their: (i) data and analytic infrastructure (including sources of data), (ii) HIT and HIE infrastructure and tools, and (iii) other resources used and needed to support population health management activities (including an identified roles of ACHs in Population Health Management activities). HCA staff will summarize and bring information back to the Medicaid Transformation Priorities Steering Committee. | MMCO Contract Language 14.2 Population Health Management: Plan The Contractor shall develop a plan to address Enrollee needs across the continuum of care, and ensure services are coordinated for all Enrollees. The plan shall be reviewed by HCA during the annual monitoring review. The Population Health Management plan shall include at a minimum the following focus areas: 14.2.1 Keeping Enrollees healthy; 14.2.2 Managing Enrollees with emerging risk; 14.2.3 Enrollee safety and outcomes across settings; 14.2.4 Managing multiple chronic conditions; and . 14.2.5 Managing individuals with multiple service providers (e.g., physical health and behavioral health) The Contractor’s Population Health Management plan shall establish methods to identify targeted populations for each focus area and include interventions that meet the requirements of NCQA and the subsections below. The Contractor’s Population Health Management plan shall take into account available and needed (i) data and analytic infrastructure, (ii) HIT and HIE infrastructure and tools, and (iii) other resources needed to support population health management activities 14.3.5 The Contractor will use other data sources to identify enrollees who need care coordination and care management services, including but not limited to: 14.3.5.1 Enrollees that have had contact with crisis services 14.3.5.2 Review of administrative data sets, such as PRISM; 14.3.5.3 Children with elevated blood lead screen levels; 14.3.5.4 Indicators of potential for high risk pregnancy; 14.3.5.5 Enrollees with unmet care needs or evidence of being underserved; 14.3.5.6 Claims or encounter data; 14.3.5.7 Pharmacy data; 14.3.5.8 Laboratory data; 14.3.5.9 Electronic health records; 14.3.5.10 Data in the Clinical Data Repository; and/or 14.3.5.1110 Results of Contractor-specific algorithms.
8-04 |  | MMC Care Coordination Services | Q1-Q2: HCA HIT Section staff, in collaboration with Policy and DBHR staff, will engage MCOs in a Workgroup to: (i) identify how plans define: service coordination, care coordination services, care management, and complex care management services; and (ii) identify, prioritize, and methods to address gaps in an interoperable HIT infrastructure to support these services, including electronic care plans and closed loop referrals. HCA staff will summarize for the Medicaid Transformation Priorities Steering Committee gaps identified by the Workgroup and suggested methods for addressing these gaps. HCA staff will send information to MCOs about the Workgroup no later than mid-January 2020. | MMCO Contract Language Section 14.6.14 requires the Contractor to participate in a Workgroup with HCA to explore the extent to which the HIT Infrastructure can be developed to support the many tasks in Section 14.6.1 through 14.6.9. The tasks include, for example: - offering Wellness and Prevention services - Ensuring access to medically necessary behavioral health, or physical health services and coordination with entities that provide mental health, SUD services, and oral health services - Ensuring access to community-based services, - Promoting Continuity of Care - Improving access to care or to services that address social needs.
8-05 |  | MMC Care Management Services | See MMC Care Coordination Services (row 52) | MMMCO Contract Language 14.7 Care Management Services. The Contractor shall implement activities for Enrollees identified as requiring Complex Case Management (CCM), or those with multiple chronic conditions. 14.7.1 Support of a person-centered approach to care in which Enrollee’s needs, strengths, and preferences play a central role in the development and implementation of the care plan by: 14.7.1.7 Supporting, to the maximum extent possible, the development and implementation of, and updates to interoperable electronic care plans, that include at a minimum information in section 14.7.4.1 through 14.7.4.3. The contractor shall ensure that such care plans are transmitted to the CDR when developed and updated. 14.7.2 The Contractor shall participate in a workgroup with HCA to assess the utilization of interoperable care plans and barriers to using electronic care plans
8-06 |  | Patient Access to Electronic Health Information | Q1- Q2: Following publication of the ONC and CMS final rules on patient access to electronic health information, HCA staff and leadership will review the final rule and develop a strategy for implementing requirements.
8-07 |  | Communication Strategy HIE, including the CDR | Q2 - Q3 HCA/HIT Section staff, in collaboration with HCA Data Governance and Privacy staff, will develop a communication strategy to inform and engage: (i) providers (in collaboration with ACHs) and (ii) consumers in health information exchange, including awareness and uses of the Clinical Data Repository (e.g., include real time demonstrations of CDR functionality). The Communication Strategy will take into account the HCA Data Strategy and final rules published by the Federal Government related to consumer initiated information exchange. | 2019 task
8-08 |  | 1st responders/Community Paramedicine | Q1-Q2: HCA HIT Section and Policy staff will collaborate with ACHs to identify opportunities to integrate 1st responders/Community Paramedicine in HIE activities (e.g., use of: closed loop referral, CM tools, Digital Health Commons).
Registries
9-01 |  | Administer Public Health Registry Onboarding | Leveraging funds available through the SUPPORT Act, HCA HIT Section staff will support providers in meeting the Promoting Interoperability Program requirement to contribute data to a state registry (i.e., use of the PMP registry). Support will continue through the end of the designated administrative funding period for HITECH.
Adding Clients to CDR
10-01 |  | Enable Addition of non-tribal FFS Clients to CDR | Q2 - Q3 Contingent on the availability of a consent management tools that enables the segregation of data, HIT Section staff will: (i) work with HCA P1 to produce daily non-tribal FFS extracts and transmit to the CDR; (ii) support work by OHP to create and implement an interface to receive or daily updates for non-tribal FFS eligibility, and (iii) identify and establish a sustainable funding mechanism. Q4: HIT Section staff will coordinate and consult with Tribal partners regarding the addition of FFS client data .
Adding CDR Users
11-01 |  | CDR onboarding | Q3-4: Contingent on the availability of funds, HIT Section staff will offer CDR onboarding incentives and technical assistance to BH and LTC providers.
11-02 |  | Jail Transition Services | Q2 - Q3: HCA HIT Section, Policy, and DBHR staff, in collaboration with Department of Corrections and WASPC (Washington Association of Sheriffs and Police Chiefs), will identify tools and opportunities/ barriers to provide: (i) jail medical staff access to health information for persons who become incarcerated and (ii) community-based health providers/care managers/ payers access to health information for persons released from incarceration. Tools to be considered include: providers' EMRs, EDIE/PreManage, CDR, CCDs. Barriers and opportunities include technology, policies, and workflow.
Adding CDR Functions/ Quality
12-01 |  | Update HIE Roadmap | Q2 and Q4: Update and disseminate the HIE Roadmap (vision statement) that depicts when: (i) additional HIE functionality will be added (e.g., consent management solution, inter-state PDMP data sharing); (ii) additional populations will be added to the CDR; and (iii) multiple methods of HIE will be aligned. The HIE Roadmap will take into account (but is not limited) to HIE functionality required in the Support Act. The Roadmap will be updated every 6 months. | 2019 project continuing
12-02 |  | Deploy Reporting Features in CDR | Q4: December 31st, 2020, the OHP will coordinate with HCA to develop a strategy for leveraging data visualization and reporting tools for CDR data. Deployment of analytical capability is contingent upon approval of the Agency’s Data Governance approval of tool and intended usage. Q1: OHP will coordinate with the HCA on a discussion of analytical support priorities. Q2- Q4: OHP will coordinate with HCA to develop tools capable of creating reports which have been appropriately aggregated to meet HCA’s data governance standards for Category 2 data (i.e. non-identifiable data). | 2019 project continuing
12-03 |  | Deploy Query and API functionality in CDR | HCA will determine what system-to-system access is appropriate for clinical and claims content in the CDR and as appropriate, enable system-to-system access to CDR data through established data access standards. Task will identify (in consultation with service providers) and support prioritized query access (e.g., access to full C-CDA documents, portions of a clinical record through a FHIR API, and portions of the administrative data through a claims-based API). | 2019 project continuing
12-04 |  | Data Quality Improvement Efforts | HCA and OneHealthPort (OHP) will work to improve the quantity, quality, and standardization of data elements in the clinical documents submitted to the CDR. HCA will direct the prioritization of this work, including focusing on physical health, mental health and Substance use disorder data. | 2019 project continuing
12-05 |  | Design/Develop Smart Form Use Cases. | HCA will design and develop four use cases for providers/entities with limited HIT/EHR technology to (i) create and (ii) transmit and/or (iii) download information to/from the CDR. Initial use case may focus on health action plans (HAPs). If additional funds become available, use cases could focus on discharge plans/ summaries, assessment, screening and intact tools.
12-06 |  | SDOH data | Leveraging the HCA Data Strategy, activities undertaken via the Medicaid Transformation Priorities Workstreams, and other related activities being undertaken by HCA; HCA HIT Section and Policy will: (i) identify use cases, needed policies/guidance, needed data elements, and/or data sources for the exchange and re-use of SDOH data (including the utility/need for FHIR-based APIs to transmit a subset of SDOH data elements) and (ii) consider data used to inform the development health equity strategies and solutions. Deliverables will be advanced to the Medicaid Transformation Steering Committee and agency leadership. | 2019 project continuing
12-07 |  | Develop Standardized Shared Care Management Tools/Functions | In collaboration with ACHs and providers, HCA will identify existing HIT standards and interoperable care management tools that could be deployed in conjunction with the HIE and CDR (e.g., consider: shared care planning, post-discharge care management for patients recently discharged from inpatient mental health facilities). | 2019 project continuing
12-08 |  | Develop Standardized Discharge Summary | HCA will develop a Discharge Summary API (for use by providers with limited technology adoption) and guidance that conforms with the Discharge Summary C-CDA specifications adopted for the 2015 version of Certified EHRs. Guidance will consider issue of diagnosis (or chief complaint) inconsistency across hospitals.
Provider Education
13-01 |  | Medicaid MCOs will provide ongoing provider education regarding health IT and health information exchange | Medicaid MCOs will provide (through MC-Tracker) semi-annual reports entitled, HIT/HIE Technical Assistance Report, describing the number and type of providers and support staff participating in provider education related to HIT/HIE and the participants' satisfaction from the training process. HCA/HIT Section staff will include a semi-annual update via the HIT Operational Planning meetings on the MMCO reports entitled, HIT/HIE Technical Assistance Reports. HCA HIT staff will make available to MCOs: (i) at least once every 6 months, resources that MMCOs could use to provide training/technical assistance to physical health, behavioral health, and tribal health care providers (ii) at the standing HCA/Health IT Operational Plan Update meetings, any key HIT/HIE activities at the federal and state . Specific updates that MMCOs should communicate to their network providers may be highlighted during these standing meetings. | 2020 MMC contract: Section 9.11 requires that Contractors maintain records of the number and type of providers and support staff participating in provider education, and their satisfaction from the training process. 9.11.1.19 The Contractor, in collaboration with the HCA, shall keep providers (including physical health, behavioral health, tribal health care providers) informed of and provide technical assistance on; - Health IT and interoperable health information exchange at the State and Federal levels; - Current and anticipated health information exchange and use via the Clinical Data Repository; and - Information about Certified EHR Technology and Certified Health IT available through the Office of the National Coordinator for Health Information Technology (ONC). The contractor shall provide semi-annual reports describing the information / technical assistance provided, and type and number of participating providers 14.5 Bi-Directional Behavioral and Physical Health Integration 14.5.1 The Contractor shall promote bi-directional behavioral and physical health integration through education, training, financial, and nonfinancial incentives consistent with Section 14 of this Contract, recommendations of the Bree Collaborative, and other network initiatives to promote integrated care including, but not limited to: 14.5.1.6 Use of electronic health records, Clinical Data Repository (CDR), decision support tools, client registries, data sharing, Care Coordination, wellness initiatives targeting high-risk behavioral health populations, and other similar program innovations.
13-02 |  | Technical assistance to providers on health IT to facilitate the adoption of value based purchasing | Q4: HCA will use survey results from the annual provider and MMC plan survey on value based purchasing to identify TA needed by different types of providers (e.g., BH providers, rural providers) on the use HIT/HIE/interoperability/other topics to support VBP. HCA, in collaboration with ACHs and MMCO, will identify options and opportunities to deliver the TA.
Tribal Engagement
14-01 |  | Have conversations with Tribes about Exchanging Health Information | HCA will continue conversations with Tribal partners and the AIHC on the value of HIE, the need to limit/protect access to tribal members health information, how the technical solution to be deployed for consent management could be extended to protect tribal members health information in the CDR, and solicit Tribal/AIHC input on HIE use cases. | 2019 project continuing
14-02 |  | Assist Tribes exploring EHR replacement and system integration | Upon request by AIHC and/or tribal partners, HCA will provide technical assistance to Tribes exploring EHR replacement and system integration, including w/ respect to BH provider acquisition and use. | 2019 project continuing
14-03 |  | Support Tribal Adoption of CDR | HCA will work with our Tribal Government partners to identify potential use cases for integrating Tribal populations into the CDR. | 2019 project continuing
14-04 |  | Discuss TARGET replacement with Tribal providers | HCA will discuss TARGET system replacement with Tribal partners, including: - Identifying gaps created by moving away from Target system - Identifying requirements to ensure system replacement doesn't break existing processes by tribal providers
Behavioral Health Integration
15-01 |  | Technical Assistance to BH Providers on CEHRT adoption and use | HCA HIT Section, DBHR, and Policy, in conjunction with ACHs, will provide technical assistance to behavioral health providers to support the SUD IMD waiver and the MH IMD waiver, including (i) adoption and use of CEHRT and (ii) use of the PDMP. | 2019 project continuing
|  | Identify and support the use of potential funding sources for BH providers use of HIT/HIE | HCA will seek to identify potential funding sources to promote behavioral health providers adoption and use of certified EHR technology and health information exchange. (see row 9) | 2019 project continuing
|  | Streamline SAMHSA Reporting | As required under the SAMHSA CAP to develop standardized definitions and formats of the required data set that, in addition to minimizing the data burden on behavioral health providers, will meet health information technology interoperability goals. Ensure streamlined data set identified for SAMHSA BH Reporting includes data elements required for other required reporting activities (e.g., legislative reporting, involuntary commitment reporting, ASO reporting) | 2019 project continuing
Substance Use Disorder Health IT
|  | eConsent Management Tool | HCA will develop and pilot an electronic consent management solution that can be used to support the exchange of information subject to 42 CFR Part 2 and allow for the appropriate redisclosure of this information. (see row 13) | 2019 project continuing