## Tasks
Number | Category | Title | Description (if more detail than title) | HIT Ops Plan Year | Start Date | End Date | HCA Owner
1 | Data and Governance
1-01 |  | Policies/guidance regarding clinical and claims data, including data in the CDR. | Develop/clarify needed policies/guidance/procedures for accessing, using, and complying w/ policies/procedures regarding HCA data assets (i.e., clinical and claims data (including data in the CDR)) in accordance with the Data Governance Process through the DUC. Develop/identifty and provide to ACHs guidelines/educational resources regarding HIPAA and access to PHI. | 2019 | Q1 2019 | Q2 2019 | EDMA/DMG /Privacy/HIT Section
1-02 |  | Role-based access policies for clinical, social, and claims data | In collaboration with ACHs, (i) identify use cases involving ACHs and service providers and (ii) develop role-based access guidelines for accessing clinical, SDOH, Health Action Plans, and claims data. Guidance will provide clarity on data access by role and source of data (e.g., between CDR and CCS). Roles to be considered include roles for licensed health care providers (e.g., physicians, nurses, social workers, care managers, correctional health workers), non-licensed care providers (e.g., CHWs, personal care workers/aides) and organizations (e.g., care management organizations, community-based organizations, local public health agencies). As appropriate, develop an MOU between HCA and OHP regarding these policies. | 2019 | Q1 2019 | Q2 2019 | EDMA/DMG/ Privacy/ HIT Section/HW
1-03 |  | Enterprise Governance | HCA, through the Health and Human Services multi-agency Enterprise Governance (EG) process (involving HCA, DoH, DSHS, DCYF, HBE) will: 1. identify and select business cases that involve the exchange of HCA data assets; 2. consider for selected use cases: data governance policies and procedures regarding access, use, and exchange) 3. integrate HIT/HIE (including the CDR) considerations into the selected use case; and 4. formalize the MITA connection to the business case (e.g., the PDMP connection to MMIS). | 2019 | Q1 2019 | Q4 2019 | EDMA
1-04 |  | Develop process for incorporating successes from evaluation work (SIM, MTP, etc.) | Using the SIM evaluation and MTP Independent External Evaluation outcomes regarding data analysis and health information technology/HIE, develop routine communication methodologies to share successes for regular program improvement, including communications to ACHs for dissemination to providers and program/pilot implementation as applicable. | 2019 | Q1 2019 | Q3 2019 | ARM
2 | Master Person Index
2-01 |  | Draft MPI White Paper and Implementation Plan for Enterprise Governance decision making | Draft an MPI White Paper for decision making for the Health and Human Services multi-agency Enterprise Governance (EG) process (involving HCA, DoH, DSHS, DCYF, HBE), The draft MPI White Paper will take into account need for MPI (e.g., use of an MPI in eligibility and enrollment and the PDMP (see Tasks 06-03 and 14-08)) and will take into account input from non-state entities selected by HCA for an advisory role given their work on similar MPI efforts. Develop project implementation plan with key decision points. | 2019 | Q1 2019 | Q4 2019 | HIT Section
3 | Provider Directory
3-01 |  | Draft Provider Directory white paper and implementation plan for Enterprise Governance decision making | Draft a Provider Directory White Paper for decision making for the Health and Human Services multi-agency Enterprise Governance (EG) process (involving HCA, DoH, DSHS, DCYF, HBE). The draft Provider Directory White Paper will take into account need for such directory (e.g., use of a Provider Directory in the PDMP (see Tasks 06-03 and 14-09)) and will take into account input from non-state entities selected by HCA for an advisory role given their work on similar provide directory efforts. Develop project implementation plan with key decision points. | 2019 | Q1 2019 | Q4 2019 | HIT Section
3-02 |  | Time and distance standards for provider networks | Identify time and distance standards for inclusion in MCO contracts. This will require the provider directory to allow geo-coding. | 2019 | Q3 2019 | Q4 2019 | MPOI Division
4 | Payment Models and Sources
4-01 |  | Provider Assignment/Provider Attribution | Identify various patient /provider attribution methodologies used by MCOs to assign patients to providers. Recommend patient/provider attribution/assignment methodology to support alternative paymet models. Develop an approach to align Medicaid attribution methodologies across MCOs and then align with PEB and SEB attribution methodologies. | 2019 | Q3 2019 | Q4 2019 | VBP/MPOI
4-02 |  | MCO HIE incentives | HCA staff will work with CMS and ONC for what contract language could be included and if additional funding can be supplied as part of MCO rate determination. HCA, in collaboration with ONC, CMS, and MCOs, will identify methods/mechanisms that are used/could be supported by MCOs to support the use of HIT/HIE by providers (e.g., to support prior authorization and integrated PH and BH care). This task includes the identification of additional potential incentive and penalty policies for participation with the CDR. | 2019 | Q2 2019 | Q3 2019 | MPOI/HIT Section
4-03 |  | VBP Models and HIT/HIE | Analyze for either global VBP system and/or project specific VBP models: • Whether base year payment calculations take into account HIT/HIE costs for providers participating in VBP models; and • VBP payment methods that create incentives for providers to use HIE technology to send/receive data (including to the CDR for identified use cases (e.g., transitions in care). HW/Payment Policy staff will submit to HCA polcy leadership findings of analysis and take action as appropriate. | 2019 | Q1 2019 | Q3 2019 | HW/Payment Policy
4-04 |  | Implement Payment Model 2-Rural Multipayer Payment Model | Implement VBP incentives in Rural Multipayer Payment Model that include incentives to use HIE technology to send/receive data to the CDR . | 2019 | Q1 2019 | Q4 2019 | VBP
4-05 |  | Public/Private Partnerships | Develop a white paper in collaboration with OFM to identify requirements for entering into public/private partnerships (e.g., any minimum private sector contribution, needed receipt and tracking mechanisms) and general guidelines for establishing such partnerships within HCA. Implement needed policies/accounting systems to establish public/private partnerships. Identify and pursue public/private partnership opportunities. | 2019 | Q2 2019 | Q3 2019 | HIT Section/OFM
5 | Health Information Exchange functionality, including enhancing the CDR
5-01 |  | Identify and Synthesize Planned ACH and State HIT/HIE Investments | HCA, in collaboration with ACHs, will identify areas in which ACHs have/are planning to make HIT/HIE investments (including the provision of technical assistance), including: BH and social providers, care management tools, tools to support discharges and referrals in care, correctional health service providers, population health management tools, use of Health Commons, use of PreManage, tools to identify community/social service resources and capacity/availability. HCA will identify those areas in which the state anticipates making investments (e.g., in implementing provisions in the Support Act (e.g., linking the PDMP data with EHRs and making available incentive payments to incent the adoption and use of CEHRT by BH providers). Analysis will: identify gaps in needed interoperable HIT/HIE functionality, the need for TA (particularly for smaller providers) regarding the adoption and use of HIT/HIE (including certified EHRs), and inform HCA/ACH progress towards implementing needed HIT/HIE. Initial deliverable provided in Q2. Analysis will be updated over time. This information will inform the HIE Roadmap and updates to the Roadmap (see Task 09-01). | 2019 | Q1 2019 | On-going | HIT Section
5-02 |  | Multiple Methods of HIE | Develop a white paper describing the need/value and multiple methods of HIE (e.g., CDR, EDIE/PreManage, state HIE, local exchange mechanisms) and develop a strategy and timeline for aligning multiple methods of HIE to support care and population health management. Information will be shared across ACHs. Information will be shared across ACHs. See Task 09-01. | 2019 | Q1 2019 | Q2 2019 | HIT Section
5-03 |  | Closed loop referral and Population Health Management | In collaboration with ACHs and their partnering providers (e.g., acute care, primary care, BH, FQHC, jails) identify and produce written description of emerging / best practices across communities to provide HIT-enabled integrated person-level care. Describe practices and opportunities, including the use of technology to support close-loop referral processes, identify and stratify high risk patients, and support health information sharing. | 2019 | Q3 2019 | Q4 2019 | HIT Section
5-04 |  | Strategy for Community/Provider Engagement on HIE, including the CDR | Develop a communication strategy to inform and engage providers (in collaboration with ACHs) in health information exchange, including awareness and uses of the Clinical Data Repository (e.g., include real time demonstrations of CDR functionality). Include methods for demonstrations as new HIE/CDR functionality is added. | 2019 | Q1 2019 | On-going | HIT Section/Communications
5-05 |  | Strategy for Community/Consumer Engagement on HIE, including the CDR | Develop a communication strategy to inform and engage patients/clients/consumers in health information exchange, including awareness and uses of the Clinical Data Repository | 2019 | Q1 2019 | Q2 2019 | HIT Section/Communications
5-06 |  | Security practices for HIT/HIE | HCA will disseminate an FAQ document that points to sites/sources for standards for best security practices for HIT/HIE. The document will be developed with input from MCO IT Security Officers and Office of Cyber Security. The paper will reference OHP and MCO security practices and other selected HIE services. | 2019 | Q1 2019 | Q2 2019 | HIT Section
5-07 |  | Telehealth | HCA, in collaboration with ACHs, will identify barriers to the use of telehealth, including in remote areas of the state, and identify options and funding sources (including provisions in federal law (e.g., The Support Act)) to address these barriers. |  | Q1 2019 | Q2 2019 | HW/CQCT
6 | Registries
6-01 |  | Administer Public Health Registry Onboarding | Support providers in meeting the Promoting Interoperability requirement to contribute data to a state registry. Support will continue through the end of the designated administrative funding period for HITECH. | 2019 | Q2 CY2014 | Q3 2021 | HIT Section
6-02 |  | SUPPORT Act: PDMP | Explore the feasibility of using 100% FMAP (added to Sec. 1944(f) in Sec. 5042 of The Support Act) to design, develop, or implement enhancements for a qualified PDMP. Clarify availability of MMIS enhanced funds for Maintenance and Operation costs of a "qualified PDMP" required in Medicaid (through the Support Act). As appropriate and needed, advance IAPD. Identify, prioritize and implement PDMP enhancements required in The Support Act, including: those to support the SUD HIT Plan in the IMD Waiver, including integrating information into the workflow of a covered provider, which may include the electronic system used by the covered provider (such as an EHR). | 2019 | Q4 2018 | Q2 2019 | EDMA/HIT Section
6-03 |  | Support Access to PDMP through CDR | Contingent on the availability of funds, develop a function to allow providers within the CDR clinical portal to access the DOH-operated PDMP, including enabling the integration of PDMP data into providers' EHRs. This will involve efforts to establish patient/provider matching and shared user authentication across the systems. In addition, this will require development of (i) an interface between the CDR and the HIE/PDMP and (ii) an open-source interface between the CDR and CEHRTs. See related tasks: 02-01, 03-01, 14-07. | 2019 | Q4 2018 | Q2 2019 | HIT Section
6-04 |  | Support Act: PDMP Guidance | HCA, in collaboration with DoH, shall pursue/obtain guidance/support from CMS, CDC, and ONC for PDMP provisions in the Support Act, including guidance/support on provisions under Sections 7162 and 5042 (and other provisions) of the Support Act (e.g., provisions related to: ensuring the highest level of ease in use of and access to PDMP; integrating PDMPs within EHRs and HIT infrastructure; linking PDMP data to other data systems within the State; improving the interstate interoperability of PDMPs; improving the ability to include treatment availability resources and referral capabilities within the PDMP; quality measures and reporting requirements). | 2019 | Q4 2018 | Q4 2019 | HIT Section/DoH
6-05 |  | Integrate Other Public Health Registries | Integrate additional public health registries into the CDR (e.g., creating interfaces to existing databases or otherwise making available data from registries in the CDR). Potential registries include the immunization, cancer, and electronic lab reporting registries. | 2019 | Q3 2019 | Q3 2021 | HIT Section
7 | Adding Clients to CDR
7-01 |  | Enable Addition of FFS Clients to CDR | Currently, the CDR contains MCO enrolled clients, and not FFS clients. This project will require establishment of a client eligibility interface, updates to existing claims interfaces with OHP, and establishment of a sustainable funding mechanism. The addition of FFS client data will be coordinated in consultation with Tribal partners. | 2019 | Q3 2019 | Q2 2020 | HIT Section
8 | Adding CDR Users
8-01 |  | CDR onboarding | Offer CDR onboarding incentives and technical assistance to BH and LTC providers, contingent on funding. | 2019 | Q3 2019 | Q4 2019 | HIT Section
8-02 |  | Jail Transition Services | Leveraging guidance produced under Task 1-02 and information gathered in Task 5-01, HCA in collaboration with Department of Corrections and partnering providers in ACHs, will identify tools and opportunities/ barriers to provide: (i) jail medical staff access to health information for persons who become incarcerated and (ii) community-based health providers/care managers/ payers access to health information for persons released from incarceration. Tools to be considered include: providers' EMRs, EDIE/PreManage, CDR. Barriers and opportunities include technology, policies, and workflow. | 2019 | Q3 2019 | Q4 2019 | HIT Section/DoC
8-03 |  | 1st responders/Community Paramedicine | HCA will collaborate with ACHs to identify opportunities to integrate 1st responders/Community Paramedicine in HIE activities. | 2019 | Q1 2019 | Q3 2019 | HIT Section/ DoH/CQCT
9 | Adding CDR Functions/ Quality
09-01 |  | Update HIE Roadmap | Update and disseminate the HIE Roadmap (vision statement) that depicts when: (i) additional HIE functionality will be added (e.g., consent management solution,inter-state PDMP data sharing); (ii) additional populations will be added to the CDR; and (iii) multiple methods of HIE will be aligned. The HIE Roadmap will take into account (but is not limited) to HIE functionality required in the Support Act. The Roadmap will be updated every 6 months. | 2019 | Q1 2019 | Q3 2019 | HIT Section
9-02 |  | Deploy Reporting Features in CDR | Identify (in collaboration with service providers) and deploy reporting capabilities in the CDR to provide mainstream, user-oriented reporting to providers, including summary reports of clinical data. | 2019 | Q4 2018 | Q4 2019 | HIT Section
9-03 |  | Deploy Query and API functionality in CDR | Determine what system-to-system access is appropriate for clinical and claims content in the CDR and as appropriate, enable system-to-system access to CDR data through established data access standards. Task will identify (in consultation with service providers) and support prioritized query access (e.g., access to full C-CDA documents, portions of a clinical record through a FHIR API, and portions of the administrative data through a claims-based API). | 2019 | Q4 2018 | Q4 2019 | HIT Section
9-04 |  | Data Quality Improvement Efforts | HCA and OHP will work to improve the quantity, quality, and standardization of data elements in the clinical documents submitted to the CDR. Going forward, work will also include the identification and implementation of options to improve quality of MH and SUD data. | 2019 | Q3 2018 | Q4 2019 | HIT Section
9-05 |  | PAMI+ Report for Healthcare Providers | HCA, in collaboration with OHP and clinical users, will determine the best method(s) for accessing and distributing CDR data (e.g., developing an interface for the CDR for BH/LTC providers and correctional health service providers (such as a PAMI+ report) | 2019 | Q2 2019 | Q3 2019 | HIT Section
9-06 |  | Design/Develop Smart Form Use Cases. | Design and develop four use cases for providers/entities with limited HIT/EHR technology to create and transmit and/or download information to/from the CDR. | 2019 | Q2 2019 | Q3 2019 | HIT Section/ DBHR/ ALTSA
9-07 |  | SDOH data and CDR | Review options for collaborating with external vendors for a statewide SDOH template. Develop a standard template for transmitting a subset of SDOH data elements (that have already been linked to HIT vocabularies) and a CDR interface to receive this content. | 2019 | Q2 2019 | Q3 2019 | HIT Section/ EDMA/DMG / HW
9-08 |  | Develop Standardized Shared Care Management Tools/Functions | In collaborration with ACHs and providers, HCA will Using existing/available HIT standards, identify interoperable (i.e., linked to HIT standards) care management tools/functions that could be deployed in conjunction with the HIE and CDR (e.g., consider: shared care planning, post-discharge care management for patients recently discharged from inpatient mental health facilities). | 2019 | Q3 2019 | Q4 2020 | HIT Section
9-09 |  | Develop Standardized Discharge Summary | Develop a Discharge Summary API (for use by providers with no/limited technology adoption) and guidance that conforms with the Discharge Summary C-CDA specifications adopted for the 2015 version of Certified EHRs. Guidance will consider issue of diagnosis (or chief complaint) inconsistency across hospitals. | 2019 | Q2 2018 | Q2 2020 | HIT Section/DBHR
9-10 |  | Medication Prior Authorization | Leveraging previous efforts and ONC Strategy on Reducing Regulatory and Administrative Burden Relating to the Use of Health IT and EHRs, develop white paper on (i) policies and (ii) processes related to prior authorization in Medicaid fee-for-service and MMCOs, and options/opportunities and costs to standardize the prior authorization process across MMCOs and use health IT tools for the prior authorization process. | 2019 | Q1 2019 | Q4 2019 | MPOI/ HIT Section
9-11 |  | Increase DDA Client Data in CDR | Explore how to increase/improve data available in the CDR on DDA clients (e.g., adding claims data from ProviderOne) and if feasible, implement improvements. | 2019 | Q3 2018 | Q2 2019 | HIT Section
10 | Tribal Engagement
10-01 |  | Have conversations with Tribes about Exchanging Health Information | Continue conversation with Tribal partners on the value of HIE, the need to limit/protect access to tribal members health information, how the technical solution to be deployed for consent management could be extended to protect tribal members health information in the CDR, and solicit Tribal input on HIE use cases. | 2019 | Q2 2018 | Q4 2019 | Tribal Liaisons/HIT Section
10-02 |  | Assist Tribes exploring EHR replacement and system integration | Provide technical assistance to Tribes exploring EHR replacement and system integration | 2019 | Q2 2018 | Q2 2019 | Tribal Liaisons/HIT Section
10-03 |  | Support Tribal Adoption of CDR | This project will work with our Tribal Government partners to identify potential use cases for integrating Tribal populations into the CDR. | 2019 | Q3 2019 | Q4 2019 | Tribal Liaisons/HIT Section
11 | EHRs
11-01 |  | Administer EHR Incentive Project | Continue to support HITECH EHR incentive payments to eligible hospitals and professionals. Support is expected to continue through the end of the designated audit funding period for HITECH. | 2019 | Q1 2011 | Q3 2023 | HIT Section
12 | Behavioral Health Integration
12-01 |  | BH providers' EHR/CEHRT adoption | Support a survey of BH providers adoption/use of EHR/CEHRT. | 2019 | Q1 2019 | Q1 2019 | DBHR/HIT Section
12-02 |  | SUPPORT Act: EHR Incentive Payments to BH providers | If CMS implements authority under Section 6001 of the Support Act, HCA will pursue CMS 1115 waiver authority to make available EHR incentive payments to BH providers including: Medicare/Medicaid State psychiatric hospitals, Medicare Community Mental Health Centers, Medicaid treatment facilities, Medicaid MH or SUD providers, Medicare clinical psychologists, Medicare NPs, and Medicare CSWs. | 2019 | ASAP following CMS Guidance | ASAP following CMS Guidance | HIT Section/DBHR
12-03 |  | Technical Assistance to BH Providers on CEHRT adoption and use | Leveraging ACH HIT/HIE investments and in collaboration with ACHs, HCA will identify the need for and provide additional technical assistance to BH providers to support the: (i) adoption and use of CEHRT and (ii) use of the PDMP. | 2019 | Q2 2019 | Q4 2019 | HIT Section/ DBHR/DoH
12-04 |  | Develop and Maintain a Financial Map of Funds for BH HIT/HIE | Develop a process within HCA and DoH to identify and maintain a map of financial resources (e.g., HITECH, MMIS, The Support Act, CDC grants, MTP funds) that will be used to advance health information exchange between behavioral health and other providers. The Financial Map will be revised/updated on an ongoing basis to reflect additional funding sources. | 2019 | Q1 2019 | On-going | HIT Section/ DBHR/DoH
12-05 |  | Streamline SAMHSA Reporting | As required under the SAMHSA CAP to develop standardized definitions and formats of the required data set that, in addition to minimizing the data burden on behavioral health providers, will meet health information technology interoperability goals. Ensure streamlined data set identified for SAMHSA BH Reporting includes data elements required for other required reporting activities (e.g., legislative reporting, involuntary commitment reporting, ASO reporting) | 2019 | Q2 2019 | Q2 2019 | P10S
13 | Substance Use Disorder Health IT
13-01 |  | Guidance on complying with 42 CFR Part 2 | HCA will disseminate provider guidance on complying with 42 CFR Part 2 and consent form that could be used at the point of care to obtain patient consent to share information that is subject to 42 CFR Part 2. | 2019 | Q1 2019 | Q2 2019 | EDMA/DMG/Privacy/HIT Section
13-02 |  | eConsent Management Tool | Contingent on funding, develop and deploy an electronic consent management solution that can be used to support the exchange via the CDR of information subject to 42 CFR Part 2 and allow for the appropriate redisclosure of this information. | 2019 | Q2 2019 | Q4 2021 | HIT Section / EDMA/DMG/ Privacy
14 | SUD HIT Plan and PDMP Enhancements
14-01 |  | A. Financial map for SUD HIT Plan | HCA in collaboration with DoH will develop a financial map that identifies sources of funds (e.g., The Support Act, MMIS, CDC grants, DoH Budget) to execute the activities in this SUD HIT Plan in the IMD Waiver. Note: Timeline reflects when deliverable is due to CMS. HCA anticipates financial mapping will be an ongoing activity. | 2019 | Q4 2018 | Q1 2019 | HIT Section/ DBHR / DoH
14-02 |  | B. Enhanced interstate data sharing in order to better track patient specific prescription data | DoH will integrate PDMP data w/ the Federal RxCheck Hub. As required in Section 5042 of the Support Act, HCA and DoH will enter into a process to establish agreements with contiguous states (OR and ID) to support the sharing of data through a qualified PDMP. | 2019 | Q2 2019 | Q2 2020 | HIT Section / DoH
14-03 |  | C. Enhanced “ease of use” for prescribers and other state and federal stakeholders | Contingent on the availability of funds, HCA and DoH will support the “ease of use” of the PDMP by: (i) enhancing the usability of the PDMP web portal (e.g., reduce the number of clicks, improve navigation, show patients at risk (e.g., those with concurrent opioid and sedative prescriptions)); and (ii) entering into the process to establish interstate PDMP data sharing agreements. Enhancements to the PDMP will include: o Using SSO (in lieu of SAW) o Upgrading current and new PDMP to support the use of new standards (i.e., NCPDP SCRIPT standards) | 2019 | Q3 2019 | Q2 2020 | HIT Section/DoH
14-04 |  | D. Enhanced connectivity between the state’s PDMP and any statewide, regional or local health information exchange (Timeline 24+ months) | 1. DOH will work to reintroduce legislation (ESHB 2489) during the 2019 legislative session. 2. DoH will solicit proposals and secure new vendor to develop an API (that meets required HIT standards (NCPDP SCRIPT V. 2017-071)) for PDMP / HIE connections, including interstate data sharing of PDMP data; 3. Contingent on the availability of funds, HCA and DoH will: o work with OHP to upgrade the HIE to comply w/ current standards (NCPDP SCRIPT V. 2017-071) o work with current PDMP vendor to use current standards (NCPDP SCRIPT V. 2017-071) o secure the state funds needed for DoH staff to support increased PDMP work (e.g., work with vendor, onboarding SUD providers) o support providers ease of use of the PDMP by enabling access through the CDR portal (see Task 6-03). 4. DoH and HCA will estimate the cost of, and secure and deploy funding for onboarding SUD providers with EMRs to use the OHP/HIE and the PMP . | 2019 | Q3 2019 | Q2 2020 | HIT Section/ DoH/ DBHR
14-05 |  | E. Enhance identification of long-term opioid use correlated to clinician prescribing patterns | On a quarterly basis, DoH will provide reports to CMOs of group practices on the opioid prescribing practices for all subordinates. The reports are intended to support quality improvements and drive adoption of prescribing guidelines. Reports include comparative information on each prescriber’s opioid prescribing practice in comparison to prescribing practice in their specialty (e.g. percent of patients with chronic opioid prescriptions, percent of patients with high dose chronic opioid prescriptions). | 2019 | Q3 2019 | Q2 2020 | HIT Section/DoH
14-06 |  | G. Develop enhanced provider workflow / business processes to better support clinicians' access to the PDMP prior to prescribing an opioid or other controlled substance (Timeline: 12 months) | Contingent on the availability of funds, HCA and DoH will convene a clinical workgroup of EMR users (including PH and BH/SUD providers) to describe the desired workflow for accessing the PDMP via the CDR prior to prescribing opioids/other controlled substances. See related tasks: 02-01, 03-01, 6-03, 14-07. | 2019 | Q1 2019 | Q3 2019 | HIT Section/CQCT/DBHR/DoH
14-07 |  | H: Develop enhanced supports for clinician review of the patients’ history of controlled substance prescriptions through the PMP— prior to the issuance of an opioid prescription (Timeline: 24+ months) | Contingent on the availability of funds,HCA and DoH will develop a function to allow providers within the CDR clinical portal to access the DOH-operated PDMP, including enabling the integration of PDMP data into providers' EHRs. This will involve efforts to establish patient/provider matching and shared user authentication across the systems. In addition, this will require development of (i) an interface between the CDR and the HIE/PDMP and (ii) an open-source interface between the CDR and CEHRTs. See related tasks: 02-01, 03-01, 6-03, 14-06. | 2020 | Q1 2020 | Q4 2020 | HIT Section /DoH/OHP
14-08 |  | F. Facilitate the state’s ability to properly match patients receiving opioid prescriptions with patients in the PDMP (i.e. the state’s master patient index (MPI) strategy with regard to PDMP query) I. Enhance MPI (or master data management service, etc.) in support of SUD care delivery | Contingent on the availability of funds, in 2019, work with Health and Human Services multi-agency Enterprise Governance (EG) process (e.g., HCA, DoH, DSHS, DCYF, HBE) to: • Q1: draft a project scope that facilitates patient/provider matching. • Q2: Present draft scope to EG Exec. Sponsors • Q 3: Upon project completion (and contingent on funding) proceed w/ implementation | 2019 | Q3 2019 | Q2 2020 | EDMA/HIT Section
14-09 |  | Task I: Enhance MPI (or master data management service, etc.) in support of SUD care delivery | Contingent on the availability of funds, in 2019, work with Health and Human Services multi-agency Enterprise Governance (EG) process (involving HCA, DoH, DSHS, DCYF, HBE) to: • Q1: draft a project scope that facilitates patient/provider matching. • Q2: Present draft scope to EG Exec. Sponsors • Q3: Upon project completion (and contingent on funding) proceed w/ implementation | 2019 | Q3 2019 | Q2 2020 | EDMA/HIT Section

## Glossary
Abbreviation | Description
ACH | Accountable Community of Health: These groups bring together leaders from multiple health sectors around the state with a common interest in improving health and health equity. As ACHs better align resources and activities, they support wellness and a system that delivers care for the whole person. There are nine ACHs in the state.
ARM | Analytics, Research, and Measurement: The team within the Health Care Authority charged with developing capabilities to gather and analyze data, providing technical assistance to support community population health management and local public health needs, creating the capability across state agencies to share analytics so we can help improve population health and making data available so we can make smart changes in the health system and move to value based purchasing. This team was formally called the analytics, interoperability and measurement (AIM) team.
ASAM | American Society of Addiction Medicine is the addiction medicine society representing physicians, clinicians and other professionals
BH | Behavioral Health
C-CDA | Consolidated Clinical Document Architecture- a standardize clincal document to facilitate electronic health information exchange
CCS | Care Coordination Systems: The company that has developed a system to support the Pathways Community HUB Model
CDC | Centers for Disease Control and Prevention
CDR | Clinical Data Repository: A real time database that consolidates data from a variety of clinical sources to present a unified view of a single patient. In Washington State, this effort is lead by the Health Care Authority and is being developed by OneHealthPort
CEHRT | Certified Electronic Health Record Technology
CMO | Chief Medical Officer
CSWs | Clinical Social Workers
DDA | Developmental Disabilities Administration
DG | Data Governance: the team within HCA that manages data utilization and governance processes
DoH | Department of Health
DUC | HCA/Data Use Committee
EDIE/PreManage | EDIE and PreManage are technologies solutions offered by Collective Medical Technologies to facilitate care coordination between Emergency Departmenrs and the hospital and primary care settings
EDMA | Enterprise Data Management and Analytics: EDMA office is the group within HCA that helps manage and oversee agency decision-making based on data
ETS | Enterprise Technology Services: The division of HCA that support information technology investments
FMAP | Federal Medical Assistance Percentages: are the percentage rates used to determine the matching funds rate allocated annually to certain medical and social service programs.
HCA | Health Care Authority. The Washington State Medicaid Agency.
HIPAA | Health Insurance Portability and Accountability Act of 1996: The federal law that provides data privacy and security provisions for safeguarding medical information and the rules to enable the safe sharing of health information in support of treatment, payment and operations.
HIT Section | Health Information Technology Section: The team within HCA's Enterprise Technology Services Division that leads health information technology projects, including the electronic health record incentive program, the clinical data repository and the Health Information Technology Strategic Roadmap
HITECH | The Health Information Technology for Economic and Clinical Health (HITECH) Act: enacted as part of the American Recovery and Reinvestment Act of 2009, was signed into law on February 17, 2009, to promote the adoption and meaningful use of health information technology.
HW | Healthier Washington: The team within the HCA's policy division that is focused on improving how we pay for services, ensuring health care focuses on the whole person, and building healthier communities through a broad collaborative regional approach
MCO | Managed Care Organization
MMIS | Medicaid Management Information System (MMIS): an integrated group of procedures and computer processing operations (subsystems) developed at the general design level to meet principal objectives.
MOU | Memorandum of understanding: The formal agreement between two or more parties to ensure consistent understanding of roles and responsibilities
MPI | Master Person Index: A database used by healthcare organizations to maintain accurate medical data across its multiple entities.
NCPDP SCRIPT | National Council for Prescription Drug Programs Script: a standard created to facilitate the transfer of prescription data between pharmacies, prescribers, intermediaries, facilities, and payers.
NPs | Nurse Practitioners
OFM | Office of Financial Management: OFM's role in supplying vital information, fiscal services and policy support that the Governor, Legislature and state agencies need to serve the people of Washington.
P1 | ProviderOne: Washington State's Medicaid Management Information System (MMIS)
PAMI/PAMI+ | problems, allergies, medications, immunizations: A report to summarize critical clinical elements in health information technology
PDMP | Prescription Drug Monitoring Program
PHI | Personal Health Information: generally refers to demographic information, medical histories, test and laboratory results, mental health conditions, insurance information, and other data that a healthcare professional collects to identify an individual and determine appropriate care
SAMHSA | Substance Abuse and Mental Health Services Administration
SAW | Secure Access Washington
SDOH | Social Determinants of Health: The conditions in which people are born, grow, live, work and age that impact their health and health outcomes
SUD | Substance Use Disorder
SSO | Single Sign On
The Support Act | Substance Use-Disorder Prevention that Promotes Opioid Recovery and Treatment for Patients and Communities Act