## WA 2020-21 HIT Ops Plan
Task ID | Category | Tasks and Timeline | Related requirement
1 | EHRs
1-01 | Explore Statewide Care Coordination Solutions | Q3 2020 - Q1 2021 secure funding Q3 - Q4 2020 Participate in DOH-led and DSHS meetings re: CCS and Unite US Q4 2020 - Q2 2021 draft HCA care coordination strategy considerations will include but not limited to: - integration/alignment of HIE and CIE, take into account: - work underway in MPOI, Policy and CQCT to develop standard screenings for social determinants, - need for shared care plans, - DBHR work related to closed-loop referrals and discharge summaries - HIE on behalf of persons who transition into and out of incarceration - consideration of ACH MTP activities - consideration of Tribal providers needs Q4 2020 - Q1 2021 draft use cases (e.g., for persons w/ COD)
1-02 | Administer EHR Incentive Project | Q4 2020 - Q3 2021: support HITECH EHR incentive payments Q4 2021: Complete environmental scan comparing HIT landscape before and after Promoting Interoperability Program (PIP) (from the start of the EHR Incentive Program to current time). | 2019 project continuing
2 | Mental Health IMD Waiver
2-01 | Required MH IMD Waiver Attestation | Q2 2020: HCA submitted to CMS attestation re: adequacy of infrastructure contingent on funds | MH IMD Waiver Statement 1: Please provide an assurance that the state has a sufficient health IT infrastructure/ecosystem at every appropriate level (i.e. state, delivery system, health plan/MCO and individual provider) to achieve the goals of the demonstration. If this is not yet the case, please describe how this will be achieved and over what time period
2-02 | Required MH IMD Waiver Attestation | Q2 2020 HCA integrated MH IMD Waiver HIT Plan into state's HIT Plan. Q3 2020 and beyond: HCA will implement / refine tasks in MH IMD Waiver HIT Plan | MH IMD Waiver Statement 2: Please confirm that your state’s SUD Health IT Plan is aligned with the state’s broader State Medicaid Health IT Plan and, if applicable, the state’s Behavioral Health IT Plan. If this is not yet the case, please describe how this will be achieved and over what time period.
2-03 | Required MH IMD Waiver Attestation | Q3 2020 and beyond: HCA will assess the applicability of standards referenced in the Interoperability Standards Advisory (ISA) and 45 CFR 170 Subpart B and include these standards as appropriate in subsequent iterations of the state’s Medicaid Managed Care contracts. | MH IMD Waiver Statement 3: Please confirm that the state intends to assess the applicability of standards referenced in the Interoperability Standards Advisory (ISA) and 45 CFR 170 Subpart B and, based on that assessment, intends to include them as appropriate in subsequent iterations of the state’s Medicaid Managed Care contracts. The ISA outlines relevant standards including but not limited to the following areas: referrals, care plans, consent, privacy and security, data transport and encryption, notification, analytics and identity management.
2-04 | Financial map for BH HIT Plan | Q1-Q2 2021: DBHR, in consultation w/ HIT Section, will develop a financial map that supports increased availability/access to community-based MH services Q4 2020 through Q2 2021: DBHR will field a survey that includes an assessment of capacity and gaps of community-based BH providers (including MH) Q4 2020 though Q3 2021: DBHR will develop an APM for SUD providers, including providers that deliver MH services Q2 - Q4 2021 DBHR, in collaboration with HIT Section and other HCA sections as needed, develop plans describing state efforts to increase access to community-based mental health providers for Medicaid beneficiaries throughout the state, including through changes to reimbursement and financing policies to address gaps in access to community-based providers identified in the state’s assessment of current availability of mental health services. | MH IMD Waiver State Medicaid programs should detail plans to support improved availability of non-hospital, non-residential mental health services including crisis stabilization and on-going community-based care. The financing plan should describe state efforts to increase access to community-based mental health providers for Medicaid beneficiaries throughout the state, including through changes to reimbursement and financing policies that address gaps in access to community-based providers identified in the state’s assessment of current availability of mental health services included in the state’s application. F.a Increase availability of non-hospital, non-residential crisis stabilization services, including services made available through crisis call centers, mobile crisis units, observation/assessment centers, with a coordinated community crisis response that involves collaboration with trained law enforcement and other first responders. F.b Increase availability of on-going community-based services, e.g., outpatient, community mental health centers, partial hospitalization/day treatment, assertive community treatment, and services in integrated care settings such as the Certified Community Behavioral Health Clinic model.
2-05 | Closed Loop Referrals and e-Referrals: | Q4 2020 - Q2 2021: DBHR, in consultation with HIT Section, will field surveys of SUD and MH providers, hospitals, and other providers that includes questions regarding the use of closed loop referral systems Q1-Q2 2021: HCA/DBHR will conduct a survey of behavioral health (MH and SUD) providers focusing on integration with clinical (physical health) services. Q2 - Q3 2021: DBHR, in consultation with HIT Section, will analyze survey results and develop plan for advancing the use of closed loop referral system by providers across the care continuum | MH IMD Waiver 1.1 Closed loop referrals and e-referrals from physician/mental health provider to physician/mental health provider 1.2 Closed loop referrals and e-referrals from institution/hospital/clinic to physician/mental health provider 1.3 Closed loop referrals and e-referrals from physician/mental health provider to community based supports
2-06 | Create and use Electronic Care Plans that are interoperable | Q2--Q3 2020 DBHR will field a BH Provider Survey, that includes HIT questions, including use of creation and exchange electronic care plans Q4 2020 - Q1 2021: CQCT/DBHR will analyze findings BH Provider Survey results regarding e-care plans, closed-loop referral, and other information to improve care coordination. | MH IMD Waiver 2.1 The state and its providers can create and use an electronic care plan 2.2 E-plans of care are interoperable and accessible by all relevant members of the care team, including mental health providers
2-07 | Medical Records Transition. | Q2-Q4 2020: HCA staff (e.g., CQCT/HIT Section and Clinical, and Policy) will participate in ACH/Collective Medical (CM) Workgroup to support/advance the use of CM ADTs from hospital to community-based providers Q1-Q2 2021: HCA (HIT Section and DBHR) in collaboration with DSHS and if appropriate DOH, will support compliance with The CMS Interoperability Rule requirements and the exchange of ADT summaries upon discharge from psychiatric hospitals to community-based settings. | MH IMD Waiver 2.3 Medical records transition from youth-oriented systems of care to the adult behavioral health system through electronic communications 2.4 Electronic care plans transition from youth-oriented systems of care to the adult behavioral health system through electronic communications 2.5 Transitions of care and other community supports are accessed and supported through electronic communications MMC IMC contract language: 14.1.9 Continuity and Care Coordination for Transition Age Youth (TAY): 14.1.9.1 The Contractor shall develop a comprehensive transition plan in collaboration with other systems and providers, including agencies contracted to provide services to Youth, that identifies the Enrollee’s goals, objectives, and strategies to achieve goals. The transition plan shall take into account the following: 14.1.9.1.1 Individual behavioral and physical health needs, which may include continued services in the adult behavioral or physical health systems. The transition plan shall address the need for continuity and coordination of services and supports for the Enrollee and the Enrollee’s family and identify developmentally and culturally appropriate adult services; 14.1.9.1.2 Connections with supportive housing and supported employment services through the Foundational Community Supports program, post-secondary education, technical training, housing community support, natural supports, and cross-system coordination as needed to attain the Enrollee’s goals. 14.13.14 Prioritizing WISe For Youth Discharging From CLIP: The Contractor must prioritize access to WISe services for all youth qualified to receive WISe services that are discharging from CLIP. 14.13.15 Rehabilitation Case Management (RCM): The Contractor must provide Rehabilitation Case Management (RCM) throughout the entirety of the CLIP treatment from preadmission through discharge. RCM includes a range of activities conducted in or with a facility for the direct benefit of the admitted youth to improve treatment gains and plan for successful discharges from CLIP. Activities include: 14.17.3.1 The Contractor must complete the Uniform Discharge Tool reporting template for every individual discharging from a mental health inpatient setting hospital stay. The template, developed collaboratively with contracted MCOs and HCA, will be finalized by the end of the first quarter of 2019 and submitted afterward as described below: ... 14.17.3.5 The Contractor, in collaboration with all hospitals including state hospitals; and other facilities that provide care for individuals with 90 and 180-day civil commitments, shall develop discharge planning policies and procedures. 14.17.3.5.4 The Contractor must accept the ’honor authorization’ for SUD residential admission when services are authorized by the Enrollee’s previous MCO, in cases where an incarcerated Enrollee is authorized by one MCO but changes to another MCO upon release. 14.17.4 Care coordination and transitions between levels of care – Inpatient Treatment Agencies. 14.17.4.1 The Contractor must require that behavioral health treatment agencies develop policies and procedures that enhance care coordination, including transitions between all levels of care, by July 1, 2019. Any new policies or procedures must take effect on or before October 1, 2019. 14.17.4.2 The Contractor must work with behavioral health treatment agencies to ensure there is adequate coordination for Enrollees transitioning between various levels of treatment services to ensure continuity of care. As used in this section, “continuity of care” means the situation under which an Enrollee who is receiving services from an individual provider is entitled to receive timely and applicable follow-up services from ancillary referral agencies with the goal of providing immediate follow-up to address the holistic needs of the Enrollee. This will include, at a minimum, the following: 14.17.4.3 The Contractor must work with the Subcontractor to ensure that discharge plans and facilitation to post-discharge services are documented in the Enrollee’s electronic health record. The following must occur when the Enrollee is discharged or transitioned to a lower or higher level of care: 14.17.4.3.1 Appropriate referrals are made to a behavioral health provider and coordination with the Enrollee’s MCO. 14.17.4.3.2 Follow up appointments must be scheduled to occur within seven calendar days of Enrollee discharge and documented as such in the Enrollee’s electronic health record. Documentation must include: 14.17.4.3.2.1 Release of Information between behavioral health treatment agencies for the Enrollee; date and time of appointment; any current medications; and 14.17.4.3.2.2 If applicable, sufficient supply and compliance plan for prescribed medications is documented as part of the discharge process. 14.17.4.3.3 Enrollee’s counselor or a designated outreach coordinator at the facility, will follow up via telephone, text message, or email with the Enrollee within one week post-discharge. 14.17.5 Transition from Inpatient SUD Behavioral Health Agency. The Contractor must coordinate with Subcontractors who provide inpatient treatment to ensure referrals of Enrollees to outpatient services post-discharge from their facility. This includes the following:... 14.17.5.2.1.4 Housing. Enrollee’s housing status must be verified through the Enrollee or authorized representative and documented within the electronic health record system. When necessary, the Behavioral Health facility will refer Enrollee to housing and community support services; documentation of any referrals must be placed in the electronic health record. When the Enrollee is prescribed FDA approved medications for SUD, the provider must document efforts to obtain housing to fit the individual’s needs. 14.17.5.2.1.5 Transportation- Arrange for transportation for the individual, as needed, to scheduled appointments and recovery-based housing.
2-08 | Consent - E-Consent (sharing of sensitive health care information to all relevant parties consistent with applicable law and regulations (e.g., HIPAA, 42 CFR part 2 and state laws)) | Q3 2020: HIT Section submits a Decision Package for e-consent management (CM) pilot Q1 and Q2 2021: HIT Section secures Project Management services to release an RFI on e-consent management (e-CM) solution. Q3 and Q4 2021: Contingent on funding, procure and pilot e-CM solution. Q1 -Q2 2021: HIT Section reviews forthcoming HHS rules on 42 CFR Part 2 and consider implications for e-CM solution | MH IMD Waiver 3.1 Individual consent is electronically captured and accessible to patients and all members of the care team, as applicable, to ensure seamless sharing of sensitive health care information to all relevant parties consistent with applicable law and regulations (e.g., HIPAA, 42 CFR part 2 and state laws)
2-09 | Interoperable Intake, Assessment, and Screening tools: data is interoperable with the rest of the HIT ecosystem | Q3 – Q4 2020: HCA/CQCT, Policy, and MPOI will support the use of interoperable SDOH screening questions by Medicaid MCOs Q4 2020-Q1 2021: HCA/MPOI, in collaboration with the ACHs, MCOs, DBHR and CQCT, will identify a statewide clinical integration assessment tool that could be used by all practices and next steps and logistics for advancing a statewide use of the assessment tool. | MH IMD Waiver 4.1 Intake, assessment and screening tools are part of a structured data capture process so that this information is interoperable with the rest of the HIT ecosystem.
2-10 | Telehealth | Q2-Q4 2020: In response to the public health crisis caused by COVID-19 (CV19), HCA: - implemented telehealth service delivery and payment policies (supporting use of audio-only and audio-visual telehealth services across the care continuum including by PH, MH, and SUD providers) - distributed laptops and Zoom licenses to BH providers (and others) to support telehealth - made available training and TA to BH providers (and others) regarding use of telehealth - distributed cell phones and monthly phone and data plans to Medicaid enrolless to support their use of telehealth Q3-Q4 2020: HCA is evaluating which telehealth policies should persist beyond the public health crisis caused by CV19. Evaluation incudes quantitative analyses of use of telehealth, including by BH providers Q4 2020: HCA will secure CMS approval to use funds to acquire and distribute mobile devices for Foundational Community Supports program participants Q2-Q4 2020 thru Q2 2021: HCA co-leads, in collaboration with the Behavioral Health Institute (BHI) and the Governor's Office of Broadband, the BHI Broadband Subcommittee to identify gaps and opportunities to enhance the state's broadband infrastructure Q1 2021: HCA evaluating feasibility of renewing Zoom licenses | MH IMD Waiver 5.1 Telehealth technologies support collaborative care by facilitating broader availability of integrated mental health care and primary care Rural Health EHR
2-11 | Analytics: the state can identify patients at risk for discontinuing/stopping treatment and alerting care teams | Q4 2020 - Q2 2021: Population Health Management (PHM) Plan: HCA will explore feasibility (e.g., within HCA, RDA, MCOs) of conducting population health analytics for all clients who've stopped treatment (i.e., identify risk factors for patient who've discontinued treatment) Q3 2021: If practical, HCA will establish an MCO requirement to conduct population health analytics for clients who are at risk for discontinuing treatment Q3 2021: HCA, in collaboration with MCOs, will develop guidelines for communicating across care team members regarding persons who have been identified at risk for discontinuing treatment in order support individuals' continued engagement in services | MH IMD Waiver 6.1 The state can identify patients that are at risk for discontinuing engagement in their treatment, or have stopped engagement in their treatment, and can notify their care teams in order to ensure treatment continues or resumes (Note: research shows that 50% of patients stop engaging after 6 months of treatment ) MMCO IMC Contract language: 14.17.5.3 If the Enrollee discontinues services, the Subcontractor will document as such and attempt to facilitate transition back into the community.
2-12 | Health IT is being used to advance the care coordination workflow | See tasks: 1-01, 2-05 - 2-11 Q2-Q4 2020 and Q1 2021: HIT Section, will support coordination/collaboration between the UW BRiTE Center (that is developing digital application for first episode psychosis) and DBHR, DSHS | MH IMD Waiver 6.2 Health IT is being used to advance the care coordination workflow for patients experiencing their first episode of psychosis
2-13 | Electronic medical records capture all episodes of care, and are linked to the correct patient | Q2 2019: HCA advanced to the HHS Enterprise Coalition the MPI White Paper Q3 and Q4 2020: HCA will advance a Decision Package to implement an MPI Q3 2021 and beyond: HCA will implement an MPI Q4 2021: HCA will discuss with MPI project team timing on when considerations could begin regarding (i) linking the MPI to EMRs for clients and (ii) using the MPI to link a child’s EMR with their respective parent/caretaker medical records | MH IMD Waiver 7.1 As appropriate and needed, the care team has the ability to tag or link a child’s electronic medical records with their respective parent/caretaker medical records
2-14 | Identity Management | Q4 2021: Contingent on considerations undertaken in task 2-13 (i.e., related to HCA discussions with MPI project team timing on when considerations could begin regarding linking the MPI to EMRs for clients). | MH IMD Waiver 7.2 Electronic medical records capture all episodes of care, and are linked to the correct patient
3 | SUD HIT Plan and PDMP Enhancements
3-01 | B. Enhanced interstate data sharing in order to better track patient specific prescription data | Q4 2020 - Q4 2021: DOH will track states most often queried- once every three months
3-02 | F. Facilitate the state’s ability to properly match patients receiving opioid prescriptions with patients in the PDMP (i.e. the state’s master patient index (MPI) strategy with regard to PDMP query) | See Task 2-13. White paper includes a PDMP use case. | SUD IMD Waiver Facilitate the state’s ability to properly match patients receiving opioid prescriptions with patients in the PDMP (i.e. the state’s master patient index (MPI) strategy with regard to PDMP query)
3-03 | Task I: Enhance MPI (or master data management service, etc.) in support of SUD care delivery | Q4 2021: See Task 2-13. Contingent on considerations undertaken in task 2-13 (i.e., related to HCA discussions with MPI project team timing on when considerations could begin regarding linking the MPI to EMRs for clients). | SUD IMD Waiver Enhance the master patient index (or master data management service, etc.) in support of SUD care delivery.
3-04 | Patient/Provider Attribution | Q3 and Q4 2021: Begin planning for patient/provider attribution (taking into account MPI and Provider Directory activities)
3-05 | eConsent Management Tool | See Task 2-08 | 2019 project continuing
4 | Master Person Index
4-01 | Planning for MPI Project | Q4 2020 - Q4 2021: Planning for the HHS Coalition MPI Project continues. Implementation date TBD. | 2019 HHS Coalition-led project is evolving.
5 | Provider Directory
5-01 | Provider Directory | Q1-Q2 2021: Advance Provider Directory requirements through HCA HIT Initiatives Workgroup that will include consideration of CMS Interoperability Requirements. Q3 2021: Integrate CMS Interoperability Requirements regarding provider directory into Medicaid MCO contracts. | 2019 project continuing
6 | Payment Models and Sources
6-01 | APM for SUD | Q3 2021: HCA/DBHR will develop an APM for SUD providers, that includes use of HIT for care coordination | Section 1003 Funding: CMS Grant
7 | Data and Governance
7-01 | Access and use of CDR data for Quality Measurement | Q1 - Q2 2021: HCA Data Governance will establish CDR data access and use guidance regarding use of this data by OHP to support MCOs (and HCA) for creating clinical and population health measures. Guidance will support Task 12-03.
7-02 | Access and use of CDR data for system to system (Query) access | Q1 - Q4 2021: HCA Data Governance, in consultation with partners and stakeholders, will establish guidance for system-to-system access of clinical content in the CDR (e.g., using an enclave environment). | 2019 project continuing
7-03 | Access and use of Medicare data in the APCD | Q1 - Q4 2021: HCA Data Governance will establish guidance related to access and use of health care claims data (Medicaid, Medicare, Commercial) in the APCD for purposes of research, health cost transparency and health equity analyses.
7-04 | Access and Use of Tribal FFS Data | Q1- Q2 2021: HCA Data Governance will establish guidance related to the creation of Tribal FFS extracts and the exchange and use of such extracts in the CDR
7-05 | Access and use of data in repositories establsihed to implement the CMS Interoperability Rules | Q1-Q4 2021: HCA Data Governance, in support of HCA implementation of the CMS Interoperability Rules, will establish guidance governing access and use of data repositories.
8 | Health Information Exchange functionality, including using the CDR
8-01 | MCO Population Health Management (PHM) Plan and Allied Systems for Care Coordination | Q4 2020 - Q4 2021: HCA/CQCT including HIT Section and MPOI will review MCO (i) PHM Plans, (ii) Allied Systems for Care Coordination, and (iii) semi-annual reports entitled, "HIT/HIE Technical Assistance Report" and consider possibility of aligning and advancing innovative HIT/HIE practices | MMCO Contract Language 14.2 Population Health Management: Plan The Contractor shall develop a plan to address Enrollee needs across the continuum of care, and ensure services are coordinated for all Enrollees. The plan shall be reviewed by HCA during the annual monitoring review. The Population Health Management plan shall include at a minimum the following focus areas: 14.2.1 Keeping Enrollees healthy; 14.2.2 Managing Enrollees with emerging risk; 14.2.3 Enrollee safety and outcomes across settings; 14.2.4 Managing multiple chronic conditions; and . 14.2.5 Managing individuals with multiple service providers (e.g., physical health and behavioral health) The Contractor’s Population Health Management plan shall establish methods to identify targeted populations for each focus area and include interventions that meet the requirements of NCQA and the subsections below. The Contractor’s Population Health Management plan shall take into account available and needed (i) data and analytic infrastructure, (ii) HIT and HIE infrastructure and tools, and (iii) other resources needed to support population health management activities 14.3.5 The Contractor will use other data sources to identify enrollees who need care coordination and care management services, including but not limited to: 14.3.5.1 Enrollees that have had contact with crisis services 14.3.5.2 Review of administrative data sets, such as PRISM; 14.3.5.3 Children with elevated blood lead screen levels; 14.3.5.4 Indicators of potential for high risk pregnancy; 14.3.5.5 Enrollees with unmet care needs or evidence of being underserved; 14.3.5.6 Claims or encounter data; 14.3.5.7 Pharmacy data; 14.3.5.8 Laboratory data; 14.3.5.9 Electronic health records; 14.3.5.10 Data in the Clinical Data Repository; and/or 14.3.5.1110 Results of Contractor-specific algorithms.
8-02 | Patient Access to Electronic Health Information | Q1 -Q2 2021: HCA, led by P1OS, will contract for the development an application to expose data to third party apps as required in CMS Interoperability Rules Q3 - Q4 2021: HCA, led by P1OS, will expose data to third party apps as required in CMS Interoperability Rules
8-03 | Communication Strategy HIE | Q4 2020 -Q32021: HCA will develop and disseminate information for Medicaid enrollees regarding patient access to electronic health information Q3 and Q4 2020: HCA in collaboration WSHA, WSMA and OHP will develop vision CDR Q1 and Q2 2021: HCA will develop communication strategy for future of the CDR
9 | Registries
9-01 | Administer Public Health Registry Onboarding | Q4 2020 - Q3 2021: HCA will continue to support providers in meeting the Promoting Interoperability Program requirement to contribute data to a state registry (i.e., use of the PMP registry).
10 | Adding CDR Functions/ Quality
10-01 | Deploy Reporting Features in CDR. | Q4 2020: OHP will coordinate with HCA to develop a strategy for using data visualization and reporting tools for CDR data. Implementation of analytical tools contingent on approval by HCA. Q4 2020 - Q1 2021: OHP will coordinate with the HCA on a discussion of analytical support priorities. Q2- Q4 2021: OHP will collaborate with HCA to develop tools capable of creating reports that have been appropriately aggregated to meet HCA’s Data Governance standards for Category 2 data (i.e. non-identifiable data). | 2019 project continuing
10-02 | Data Quality Improvement Efforts. | Q4 2020-Q4 2021: OHP will coordinate with the HCA on a discussion of analytical support priorities. Q1 -Q4 2021: HCA and OHP will work to improve the quantity, quality, and standardization of data elements in the clinical documents (including those submitted to the CDR). HCA will direct the prioritization of this work, including focusing on physical health, mental health and substance use disorder data. Q1 - Q2 2021: OHP convenes discussions with key stakeholders to identify how data in the CDR could be used, consistent with HCA Data Governance guidance, to construct clinical and population health measures Q3 2021: OHP delivers to HCA a strategy that describes the use of data in the CDR, consistent with HCA Data Governance guidance, to support data quality improvement activities. | 2019 project continuing
10-03 | Transmit Tribal FFS data to CDR. | Q3-Q4 2021: Contingent on availability of an e-CM tool and devlopment of HCA Data Governance guidance, HCA will produce daily tribal FFS extracts and transmit to CDR
11 | Tribal Engagement
11-01 | Care Coordination System for Tribal Members | Q1 - Q2 2021: Explore feasibility of 100% FMAP available to tribal providers for implementing care coordination on behalf of AI/AN persons including coordination w/ non-tribal providers | 2019 project continuing
11-02 | Have conversations with Tribes about Exchanging Health Information | Q4 2020 - Q1 2021: HCA will continue conversations with Tribal partners and the AIHC on the value of HIE, the need to limit/protect access to tribal members health information, how the technical solution to be deployed for consent management could be extended to protect tribal members health information in the CDR, and solicit Tribal/AIHC input on HIE use cases. | 2019 project continuing
11-03 | Assist Tribes exploring EHR replacement and system integration | Ongoing: Upon request by AIHC and/or tribal partners, HCA will provide technical assistance to Tribes exploring EHR replacement and system integration, including with respect to BH provider acquisition and use of technology. | 2019 project continuing
11-04 | Support Tribal Adoption of CDR | Q3 2020: HCA will work with Tribal Government partners to identify potential use cases for integrating Tribal populations into the CDR. Q3 2021: Prior to release of RFP of develop an an e-CM solution, meet with Tribal Government officials to discuss anticipated RFP. | 2019 project continuing
11-05 | Discuss TARGET replacement with Tribal providers | Q1 - Q2 2021: HCA will discuss the need for TARGET system replacement with Tribal partners as part of Care Coordination solution (Task 1-01). Q2 2021 and beyond: If a TARGET System replacement is needed before a Care Coordination System is implemented, HCA HIT Section will work with Tribal Partners to: - Identify gaps created by moving away from TARGET system - Identify requirements to ensure system replacement doesn't break existing processes by Tribal providers